## 1_Infrastructure
1.1 k0rdent Enterprise Mothership (GCP-hosted)
Component | Minimum Spec | Recommended | Status | Column1 | Column2
Manager/Control Plane Nodes | 4 vCPU, 8 GB RAM | 8 vCPU, 16 GB RAM |  |  | 4 nodes in GCP
Worker Nodes | 3 nodes, 4 vCPU, 8 GB RAM | 3 nodes, 8 vCPU, 16 GB RAM
Root Disk (per node) | 100 GB SSD | 200 GB SSD
OS | Rocky Linux 9.6 or RHEL 10.1 | RHEL10.1 |  | GCP/On-prem
Kubernetes Distribution | k0s (latest stable and Supported) | k0s Latest Stable and Supported
Node-to-node connectivity | Full mesh, low latency | < 10ms intra-cluster
1.2 k0s Child Clusters
Component | Minimum Spec | Notes | Status
Nodes per cluster | 3 (combined control+worker) | Mirrors store NUC topology
vCPU per node | 4 vCPU | Allocated from Scale HyperCore KVM
RAM per node | >= 8 GB |  |  | Start with 4 cpu and 8GB based on Apps running
Root Disk per node | 50 GB | Thin-provisioned from Scale HCI SSD pool
OS | Rocky Linux 9.x | Rocky 9.2 or 9.4 confirmed installed. |  | Rocky 9.6
Hypervisor | Scale HyperCore (KVM-based) | Confirmed production hypervisor
Hardware | ASUS NUC | Per architecture diagram
Minimum cluster count for PoC | 2 child clusters | Template reusability
1.3 KOF Additional Compute
Component | Additional Overhead |  | Status
KOF stack on mothership | +2 vCPU, +4 GB RAM across worker pool |  |  | Deprecation of Ngnix, New version in future for KOF
Persistent storage for metrics/logs | Minimum 50 GB per retention window |  |  | Not in scope for poc, integrate with opensearch AAP
Grafana accessibility | Ingress or port-forward confirmed working

## 2_Storage
2.1 Mothership Storage
Requirement | Spec | Status
etcd data volume | Dedicated SSD-backed volume, minimum 20 GB
Container image cache / containerd | Minimum 50 GB per node
KOF metrics retention (Prometheus) | Minimum 50 GB
Log aggregation storage | Minimum 20 GB
OCI/Helm chart cache | Minimum 100 GB
/var/lib/kublet/ | 64
2.2 Child Cluster Storage
Requirement | Spec | Status | Column1 | Column2
Local OS + containerd storage | Minimum 50 GB SSD per node
Persistent Volume for Keycloak | Minimum 10 GB per cluster via CSI driver
Scale Computing CSI driver | Installed and validated |  | Scale CSI drivers check | Scalecomputing setup a call (Satish has point of contact)
StorageClass configured | Default StorageClass pointing to Scale HCI pool
PVC provisioning tested | Dynamic PVC creation confirmed working
2.3 Shared / Backbone Storage |  |  | Not Applicable
Requirement | Spec | Status | Column1
Private backbone network | Dedicated NIC for heartbeat + mirrored writes |  | Revisit as needed based on stateful/stateless
Scale HCI cluster health | All NUCs joined, storage pool healthy
VM failover validated | At least one NUC failure failover tested

## 3_Networking
3.1 IP Address Planning
Resource | Quantity Needed | Notes | Status | Column1 | Column2 | Column3
Static IPs — Mothership nodes | 6 | GCP VPC internal IPs |  | /28 | 4 x nodes
Static IPs — Child cluster nodes | 6 | On-prem LAN |  |  | 3 x nodes | Finalize the subnet req's with Todd and Kevin
MetalLB IP Pool — per child cluster | /29 | For LoadBalancer services |  |  | 1 x LB
Traefik Ingress VIP — per cluster | 1 | From MetalLB pool
k0rdent API server VIP | 1 | Reachable from all child nodes |  |  | 1 x VIP K0s
DNS entries | Multiple | Mothership API, Grafana, Keycloak
3.2 Firewall (Mothership → Child)
Port | Protocol | Purpose | Status
6443 | TCP | Child cluster Kubernetes API server
2380 | TCP | etcd peer communication
8132 | TCP | k0s Konnectivity tunnel
9443 | TCP | k0s API server alt port
22 | TCP | Remote SSH provider
10250 | TCP | kubelet metrics
443 | TCP | Registry URL (https://get.mirantis.com)
443 | TCP | Registry URL (https://get.k0s.com)
https://github.com
3.2 Firewall (Child → Mothership)
Port | Protocol | Purpose | Status
6443 | TCP | k0rdent management API
443 | TCP | HTTPS Helm/OCI registry
8132 | TCP | Konnectivity agent
2112 | TCP | KOF metrics endpoint
443 | TCP | Registry URL (https://get.mirantis.com)
443 | TCP | Registry URL (https://get.K0s.sh)
https://github.com
Rocky DNF
registry.mirantis.com
Note on A4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: for the child clusters. why 6 IPs and not 3?
Note on A5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Let's just write the number of IPs not a mask

## 4_Software
4.1 Node Prerequisites |  |  | Comments
Requirement | Notes | Status | Column1
Rocky Linux 9.x patched | dnf update -y completed
SELinux mode confirmed | Permissive or configured |  | LIST of packages required for Rocky 9.6 as per Rocky OS
firewalld configured | Ports open or disabled
swap disabled | swapoff -a
kubectl installed | Matching version
helm installed | v3.x
k0sctl installed | Bootstrap tool
SSH key auth | Admin host → nodes

## 5_Scale_HyperCore
Scale Computing HyperCore Prereqs
Requirement | Notes | Status
HyperCore version compatible | Check CSI matrix
Fleet Manager connectivity | SaaS reachable
KVM virtualization enabled | vmx/svm present
VM templates prepared | Rocky 9 cloud-init
HCI storage healthy | No degraded mirrors
CSI driver installed | Default StorageClass
Note on A6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: we should just ask for VMs ready, this might give the idea that we will provision and need cloud-init.

## 6_Keycloak
Keycloak SSO Prerequisites
Requirement | Notes | Status | Column1 | Column2
Keycloak Helm chart prepared | Internal registry
Admin credentials defined | Stored as Secret
Persistent volume available | PostgreSQL backend |  | Keycloak requirements from Shawn | Bring Shawn to the call to understand reqs
Ingress route defined | DNS + TLS
Realm/client config defined | Minimal PoC config
HTTP 200 reachability | Test before demo

## 7_RBAC
RBAC & Access Management
Requirement | Notes | Status | Column1 | Column2
Admin kubeconfig secured | Not in git
2 RBAC roles defined | Admin + Viewer |  | GCP roles -> Default | K0rdent default admin login/create password
Viewer ClusterRole tested | No cluster create/delete
Admin role operational | Full lifecycle access
Okta integration scoped | PoC or deferred
AD integration scoped | Confirm scope

## 8_Engagement
Engagement & Process
Requirement | Owner | Due | Status
PoC start date confirmed | Edwin Schneider | Mar 5 call
Success criteria recording shared | Edwin Schneider | After call
Engineering support windows defined | Michael T / Dina B | Before Mar 14
Daily risk check-ins started | Dina Belova | Mar 6
RC build confirmed | Dina Belova | By Mar 13
Lab access confirmed | Edwin Schneider + AAP IT | Before Mar 18

## 9_Go_NoGo
Go / No-Go Criteria
Gate | Condition | Owner
Lab Infrastructure Ready | Mothership + child clusters online | Michael Tillman
Registry Ready | Images mirrored to jFrog | Michael Tillman
Network Connectivity | All firewall rules open | Michael Tillman + AAP
Success Criteria Locked | Customer signed doc | Edwin Schneider
Engineering Support Secured | Support windows committed | Rikard Kjellberg